## Indicative PP Format
SKILLS STRENGTHENING FOR INDUSTRIAL VALUE ENHANCEMENT [STRIVE]
Name of Procuring Entity : Govt iti Saket meerut
Annual Procurement Plan for Financial Year : |  |  |  | 2020-2021 |  | 2021-2022
Date of Approval of Annual Procurement Plan : |  |  |  |  | 2021-01-07
Approved By/Name of Approving Authority : |  |  |  | IMC of GOVT. ITI SAKET MEERUT
S. No. | Procurement Category | Name/Description of Procurement/Selection | Estimated Cost [INR] | Results Area | Procurement Mode | Applicable Procurement Rules | Use of GEM [Yes/No] | Use of eProcurement [Yes/No] | Procurement Method | Market Approach [National/International] | Proposed Procurement Start Date | Pre-bid Conference Date [if any] | Proposed Procurement End Date | Tentative Contract Award Date | Tentative Contract Duration [Months] | Tentative Completion Date
Date [if any]
[1] | [2] | [3] | [4] | [5] | [6] | [7] | [8] | [9] | [10] | [11] | [12] | [13] | [14] | [15] | [16] | [17]
1 | Purchase of books and other learning materials | books for book bank | 400000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
2 | Furniture/Fixtures | furniture for All trades and offices | 500000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
3 | Purchase/Upgrading teaching/learning aids, Internet | Softwares and Others learning aids | 210000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
4 | TA/DA, Honorarium, hospitality expenses of teaching, Industry and Management staff | Industrry visit of trainee and teaching staff for upgrade training skill and Guest faculty related expeses | 400000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
5 | Machinery & Equipments | solar panal 20 kva with installation | 2000000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
6 | Machinery & Equipments | online ups 10kva/ 5 kva with battery | 400000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
7 | Machinery & Equipments | Sheet metal worker tool | 200000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
8 | Machinery & Equipments | Electrician Power Distribution Tools | 400000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
9 | Machinery & Equipments | universal cutting machine | 50000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
10 | Machinery & Equipments | Spining lathe | 250000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
11 | Machinery & Equipments | Glass cutter dianmod point | 25000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
12 | Machinery & Equipments | Buffing and polishing machine | 25000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
13 | Machinery & Equipments | Pillar type drill machine | 80000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
14 | Machinery & Equipments | Pipe bending machine | 50000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
15 | Machinery & Equipments | seaming machine | 75000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
16 | Machinery & Equipments | Desktop/Laptop | 600000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
17 | Machinery & Equipments | fitter trade tools as per NSQF | 300000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
18 | Machinery & Equipments | Turner trade tools as per NSQF Syllabus | 200000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
19 | Machinery & Equipments | AC squirrel cage motor with star delta starter with mechanical load | 150000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
20 | Machinery & Equipments | MRI Equipment | 80000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
21 | Machinery & Equipments | Secondary Injection set | 50000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
22 | Machinery & Equipments | Thyristor/IGBT AC motor | 150000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
23 | Machinery & Equipments | Wheel Balancing Machine | 150000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
24 | Machinery & Equipments | Wlk in cooler PUF insulated for cold col room 6X4.5X8 cft. | 450000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
25 | Machinery & Equipments | Genset Diesel Genrator 50/60 KVA | 750000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
26 | Machinery & Equipments | Spot and seam welding machine | 175000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
27 | Machinery & Equipments | Co2 welding machine complete set | 150000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
28 | Machinery & Equipments | Tig welding machine complete set | 150000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
29 | Machinery & Equipments | Nibbling mahine | 65000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
30 | Machinery & Equipments | Airconditioner Window/Split | 500000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
31 | Machinery & Equipments | tool of Machinist trade as per NSQF Syllabus | 200000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
32 | Machinery & Equipments | SS and SC centre lathe (all geared) with specification as:Centre height 150 mm and centre distance 1000 mm along with 4 jawchuck, Taper turning attachment,steadies, auto feed system, safety guard, motorized coolant system,with lighting arrangement and setof lathe tools, Motor Capacity - 3.5KW for Machinist trade as per NSQF syllabus | 200000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
33 | Machinery & Equipments | Hydraulic trainer as per instrument trade syllabus | 200000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
34 | Machinery & Equipments | Pneumatic trainer as per instrument machanic trade syllabus | 200000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
35 | Machinery & Equipments | Tractor Mechanic tool and eqipments as per NSQF syllabus | 150000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
36 | Machinery & Equipments | wireman trade tool and eqipments as per NSQF syllabus | 200000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
37 | Machinery & Equipments | Intractive Pannel/smart class/intractive board | 1000000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
38 | Machinery & Equipments | horizontal and vertical milling machine for Tool and die maker trade as per NSQF syllabus | 130000 | RA1 & RA2 | gem | State finencial procurement rules | yes | yes | Compatative/Ebid | national | 2021-04-01 | na | 30/07/2021 | 30/07/2021 | 1 Month | 30/8/2021
11265000
NOTES :
Annual Procurement Plan may be prepared on the assumption that total budget will be released
Procuring entities shall ensure that procurements are carried out as per Delegation of Financial Powers and within Categories defined as 'Eligible Expenditure' in the Operations Manual
Specifications for goods to be procured shall be as per approved specifications for that trade, approved by the Competent Authority