## Indicative PP Format
Format for submission of Indicative Annual procurement plan [STRIVE]
Name of State : Uttar Pradesh
Annual Procurement Plan for Financial Year : March 2023
Date of Approval of Annual Procurement Plan : 14/12/2021
Approved By/Name of Approving Authority : IMC of GITI SAKET MEERUT (GR09001541)
S. No. | Procurement Category | Full Name of Procuring Entity (SPIU/ ITI/ SMAC/ IC) | Name/Description of Procurement/Selection | Estimated Cost [INR] | Results Area | Procurement Mode | Applicable Procurement Rules | Use of GEM [Yes/No] | Use of eProcurement [Yes/No] | Procurement Method | Market Approach [National/ International] | Proposed Procurement Start Date | Pre-bid Conference Date [if any] | Proposed Procurement End Date | Tentative Contract Award Date | Tentative Contract Duration [Months] | Tentative Completion Date | Remarks
Date [if any]
[1] | [2] | [3] | [4] | [5] | [6] | [7] | [8] | [9] | [10] | [11] | [12] | [13] | [14] | [15] | [16] | [17] | [18] | [19]
1 | Goods | Govt. ITI Saket Meerut | Books for Various Trades | 500000 | RA 1 | Online | As Per State Financial Rules | Yes | Yes | GeM | National | 2022-01-10 | N/A | 2022-04-10 | N/A | 3 | 2022-03-31
2 | Goods | Govt. ITI Saket Meerut | Purchase of Furnitures for Various Trades | 800000 | RA 1 | Online | As Per State Financial Rules | Yes | Yes | GeM | National | 2022-01-10 | N/A | 2022-04-10 | N/A | 3 | 2022-03-31
3 | IT | Govt. ITI Saket Meerut | Uprading Teaching & Learning Aids by Introducing Interactive Boards, Internet, Website Renewal | 1500000 | RA 1 | Online | As Per State Financial Rules | Yes | Yes | Direct & by GeM | National | 2022-01-10 | N/A | 2022-04-10 | N/A | 3 | 2022-03-31
4 | Services | Govt. ITI Saket Meerut | TA/DA, Honorarium, Hospitality Expenses of Teaching, Industry & Mgmt Staff | 300000 | RA 1 | Online | As Per State Financial Rules | No | No | Direct | National | 2022-01-10 | N/A | 2021-06-10 | N/A | 5 | 2022-03-31
5 | Goods | Govt. ITI Saket Meerut | Purchase of Machinery & Equipment | 12844000 | RA 1 | Online | As Per State Financial Rules | Yes | Yes | GeM | National | 2022-01-10 | N/A | 2021-05-10 | N/A | 4 | 2022-03-31
15944000
Annual Procurement Plan may be prepared on the assumption that total budget will be released
Procuring entities shall ensure that procurements are carried out as per Delegation of Financial Powers and within Categories defined as 'Eligible Expenditure' in the Operations Manual
Specifications for goods to be procured shall be as per approved specifications for that trade, approved by the Competent Authority

## Notes
S No. | Indicative Procurement Category | Results Area
1 | Goods | RA 1
2 | Services | RA 2
3 | Misc (Please Specify) | RA 4
Use of GEM
Yes
No
Name/Description of Procurement/Selection
Details of category eg. Furniture, equipment, etc.
Market Approach
National
International